## Rollout Schedule
API HUNTING ABM — CAMPAIGN ROLLOUT v4
21 launch slots covering all 30 Dream List use case labels. 3 currently LIVE (see ABM Touchpoints sheet). 2 sequences live per week (Mon + Thu).
Week | Launch Day | Campaign | Priority | # Companies | Sales POC | Status | Source | Notes
Week 1 | Mon Apr 14 | Global API — Passive Deal (Full blast) | P0 | 946 | All SDRs | Live | v1 | Smartlead: P0-C2-Passive-New-Deals-Apr2026 (id 3178228) — ACTIVE
Week 1 | Thu Apr 17 | Customer Loyalty — Global API | P1 | 278 | Gaurav/Akshat | Live | v1 | Smartlead: P0_API_CUSTOMLOYALTY_GLOBA (id 3222599) — ACTIVE. Stalled deals + dream list combined.
Week 2 | Mon Apr 21 | Active Pipeline — Fintech/BFSI | P1 | TBD | Gaurav/Avipsa | Planned | v1 | Stalled deals; counts pending
Week 2 | Thu Apr 24 | Health & Wellness Apps (B2C) | P2 | 267 | Kishan | In Progress | v1 | Dream List label: 'Health & Welness Apps (B2C)' (typo preserved at source)
Week 3 | Mon Apr 28 | Digital / Neo Banking | P2 | 134 | Gaurav/Avipsa | In Progress | v1
Week 3 | Thu May 1 | E-Wallets & Payment Apps | P2 | 50 | Gaurav/Avipsa | Planned | v1 | Dream List label: 'E-wallets/Payment Apps'
Week 4 | Mon May 5 | Employee R&R Platforms | P2 | 121 | Kishan | Planned | v1 | Dream List label: 'Employee Rewards and Engagement platforms'
Week 4 | Thu May 8 | Market Research Agencies | P2 | 602 | Rakesh | Planned | v1
Week 5 | Mon May 12 | Employee Fringe Benefits Platforms | P2 | 29 | Kishan | Planned | v1
Week 5 | Thu May 15 | Customer Loyalty Platforms (Dream) | P2 | 98 | Akshat | Planned | v1 | Distinct from the Live P1 Customer Loyalty (Global API) running today
Week 6 | Mon May 19 | Channel Loyalty Platforms | P2 | 70 | Akshat | Planned | v1
Week 6 | Thu May 22 | Task-Based Rewards / Play-to-Earn | P2 | 59 | Akshat | Planned | v1 | Dream List label: 'Task Based Rewards/Play to Earn'
Week 7 | Mon May 26 | Cashback Platforms | P2 | 71 | Rakesh + Gaurav | Live | v1 | Smartlead: P0_API_CASHBACK_GLOBA (id 3222821) — ACTIVE since Apr 23. Launched ahead of schedule. Dream List label: 'Cashback plaforms'
Week 7 | Thu May 29 | Remittance + Fintech & BFSI Global (+BAAS) | P2 | 66 | Gaurav/Avipsa | Planned | v1 | Combined: Remittance (35) + Fintech & BFSI Global (30) + BAAS (1, ITIO)
Week 8 | Mon Jun 2 | Customer Referral Platforms | P2 | 42 | Akshat | New | v2 | Added from Dream List gap
Week 8 | Thu Jun 5 | Employee Referral Platforms | P2 | 43 | Kishan | New | v2 | Added from Dream List gap
Week 9 | Mon Jun 9 | Customer Advocacy Platforms | P2 | 22 | Akshat | New | v2 | Added from Dream List gap
Week 9 | Thu Jun 12 | Employee Advocacy Platforms | P2 | 11 | Kishan | New | v2 | Added from Dream List gap. Source label: 'Employe Advocacy platforms'
Week 10 | Mon Jun 16 | Fintech & BFSI India | P2 | 20 | Shailey/Gaurav | New | v2 | Added from Dream List gap; distinct from Global
Week 10 | Thu Jun 19 | Online Gaming & Casino Loyalty | P2 | 11 | Gaurav | New | v2 | Combined slot covering 10 fragmented Dream List labels (1 co each) + Gaming gift card re-sellers (1, Gameship). Sub-labels: Casino & Resort Loyalty Program; Casino & Resort Operator (Loyalty Program); Online & Land-based Casino Loyalty Program; Online Casino; Online Casino & Sportsbook; Online iGaming Platform; Online Poker & Casino Platform; Online Sportsbook & Casino; Online Sweepstakes Casino; Social / Online Casino; Gaming gift card re-sellers
Week 11 | Mon Jun 23 | Survey Platforms | P2 | 9 | Rakesh | New | v2 | Added from Dream List gap. Source label: 'Survery Platforms'
|  | TOTAL (P0 + P1 + P2) |  | 2949 |  |  |  | P1 Fintech/BFSI count pending from Gaurav

## ABM Touchpoints
ABM TOUCHPOINTS — LIVE CAMPAIGNS
Smartlead numbers pulled live on 2026-04-29. HeyReach + HubSpot columns = manual pull (no MCP available). Open/Click are 0 by design — tracking disabled to protect deliverability.
Campaign | Smartlead Campaign ID | Status | Leads in SL | Emails Sent | Replies | Reply % | Bounces | Unsubs | LI Touches (HeyReach) | Calls (HubSpot) | Total Touchpoints | Notes
Global API — Passive Deal | 3178228 | ACTIVE since Apr 14 | 264 / ~633 (sample) | 500 / 1265 (sample) | 6 | 1.2% | 1 | 0 | TBD — pull from HeyReach | TBD — pull from HubSpot | TBD | Smartlead figures from first stats page (500 of 1265 records). Open/click are 0 because tracking is intentionally disabled. Replies and bounces are real.
Customer Loyalty — Global API | 3222599 | ACTIVE since Apr 23 | 142 | 278 | 4 | 1.4% | 0 | 0 | TBD — pull from HeyReach | TBD — pull from HubSpot | TBD | Full data (278 of 278). Tracking disabled, so open/click are 0.
Cashback Platforms — Global API | 3222821 | ACTIVE since Apr 23 | 39 | 77 | 1 | 1.3% | 0 | 0 | TBD — pull from HeyReach | TBD — pull from HubSpot | TBD | Full data (77 of 77). Tracking disabled, so open/click are 0.

## Coverage Map
COVERAGE MAP — ALL 30 DREAM LIST USE CASES
Every label from the Dream List preserved verbatim (including source typos). Each label is mapped to a launch slot. Single-entry edge cases are visible and explicitly labelled 'Folded in' or 'NEW slot — combined'.
Dream List Label (as-is in source) | Cos | Mapped to Rollout Slot | Launch | POC | Status
BAAS | 1 | Remittance + Fintech & BFSI Global (+BAAS) | Thu May 29 | Gaurav/Avipsa | Folded in
Cashback plaforms | 71 | Cashback Platforms | Mon May 26 | Rakesh + Gaurav | LIVE since Apr 23
Casino & Resort Loyalty Program | 1 | Online Gaming & Casino Loyalty | Thu Jun 19 | Gaurav | NEW slot — combined
Casino & Resort Operator (Loyalty Program) | 1 | Online Gaming & Casino Loyalty | Thu Jun 19 | Gaurav | NEW slot — combined
Channel Loyalty Platforms | 70 | Channel Loyalty Platforms | Mon May 19 | Akshat | Planned
Customer Advocacy Platforms | 22 | Customer Advocacy Platforms | Mon Jun 9 | Akshat | NEW slot
Customer Loyalty Platforms | 98 | Customer Loyalty Platforms (Dream) | Thu May 15 | Akshat | Planned (Live as P1 today, separate scope)
Customer Referral Platforms | 42 | Customer Referral Platforms | Mon Jun 2 | Akshat | NEW slot
Digital / Neo Banking | 134 | Digital / Neo Banking | Mon Apr 28 | Gaurav/Avipsa | In Progress
Employe Advocacy platforms | 11 | Employee Advocacy Platforms | Thu Jun 12 | Kishan | NEW slot
Employee Fringe Benefits Platforms | 29 | Employee Fringe Benefits Platforms | Mon May 12 | Kishan | Planned
Employee Referral Platforms | 43 | Employee Referral Platforms | Thu Jun 5 | Kishan | NEW slot
Employee Rewards and Engagement platforms | 121 | Employee R&R Platforms | Mon May 5 | Kishan | Planned
E-wallets/Payment Apps | 50 | E-Wallets & Payment Apps | Thu May 1 | Gaurav/Avipsa | Planned
Fintech & BFSI Global | 30 | Remittance + Fintech & BFSI Global (+BAAS) | Thu May 29 | Gaurav/Avipsa | Planned
Fintech & BFSI India | 20 | Fintech & BFSI India | Mon Jun 16 | Shailey/Gaurav | NEW slot
Gaming gift card re-sellers | 1 | Online Gaming & Casino Loyalty | Thu Jun 19 | Gaurav | Folded in
Health & Welness Apps (B2C) | 267 | Health & Wellness Apps (B2C) | Thu Apr 24 | Kishan | In Progress
Market Research Agencies | 602 | Market Research Agencies | Thu May 8 | Rakesh | Planned
Online & Land-based Casino Loyalty Program | 1 | Online Gaming & Casino Loyalty | Thu Jun 19 | Gaurav | NEW slot — combined
Online Casino | 1 | Online Gaming & Casino Loyalty | Thu Jun 19 | Gaurav | NEW slot — combined
Online Casino & Sportsbook | 1 | Online Gaming & Casino Loyalty | Thu Jun 19 | Gaurav | NEW slot — combined
Online iGaming Platform | 1 | Online Gaming & Casino Loyalty | Thu Jun 19 | Gaurav | NEW slot — combined
Online Poker & Casino Platform | 1 | Online Gaming & Casino Loyalty | Thu Jun 19 | Gaurav | NEW slot — combined
Online Sportsbook & Casino | 1 | Online Gaming & Casino Loyalty | Thu Jun 19 | Gaurav | NEW slot — combined
Online Sweepstakes Casino | 1 | Online Gaming & Casino Loyalty | Thu Jun 19 | Gaurav | NEW slot — combined
Remittance | 35 | Remittance + Fintech & BFSI Global (+BAAS) | Thu May 29 | Gaurav/Avipsa | Planned
Social / Online Casino | 1 | Online Gaming & Casino Loyalty | Thu Jun 19 | Gaurav | NEW slot — combined
Survery Platforms | 9 | Survey Platforms | Mon Jun 23 | Rakesh | NEW slot
Task Based Rewards/Play to Earn | 59 | Task-Based Rewards / Play-to-Earn | Thu May 22 | Akshat | Planned
(Unassigned in Dream List — 247 rows) | 247 | TRIAGE NEEDED | Pre-launch | Naitik | Open: needs sorting before any of the above slots

## POC Summary
OWNERSHIP BY SALES POC
Sales POC | Use Cases Owned | Total Companies | Launch Window
Akshat | Customer Loyalty (Dream), Channel Loyalty, Task-Based Rewards, Customer Referral, Customer Advocacy | 291 | May 15 to Jun 9
Kishan | Health & Wellness, Employee R&R, Employee Fringe Benefits, Employee Referral, Employee Advocacy | 471 | Apr 24 to Jun 12
Gaurav/Avipsa | Digital Neo Banking, E-Wallets, Remittance + Fintech BFSI Global (+BAAS), Online Gaming/Casino, Cashback (co-owned), Customer Loyalty Live (co-owned) | 261 | Apr 23 to Jun 19
Shailey/Gaurav | Fintech & BFSI India | 20 | Jun 16
Rakesh | Market Research, Cashback (co-owned), Survey Platforms | 682 | Apr 23 to Jun 23

## Change Log
CHANGE LOG
Date | Change | Owner
2026-04-29 | v4: Coverage Map now lists every one of the 30 Dream List labels exactly as in source (typos preserved). Nothing collapsed silently. | Naitik
2026-04-29 | v4: Online Gaming & Casino Loyalty gets its own slot (11 cos covering 10 sub-labels + Gaming gift card re-sellers). | Naitik
2026-04-29 | v4: Survey Platforms gets its own slot (Mon Jun 23, Rakesh). | Naitik
2026-04-29 | v4: BAAS (ITIO, 1 co) explicitly listed as folded into Remittance + Fintech BFSI Global combo. | Naitik
2026-04-29 | v3: marked 3 LIVE — Passive Deal, Customer Loyalty (Global API), Cashback. | Naitik
2026-04-29 | v3: ABM Touchpoints sheet with Smartlead numbers; HeyReach + HubSpot TBD. | Naitik
2026-04-29 | v2: 6 launch slots added covering 7 missing use cases. | Naitik
2026-04-29 | OPEN: 247 unassigned rows in Dream List need triage before launch. | Naitik
2026-04-29 | OPEN: HeyReach + HubSpot touchpoint counts to be filled manually for Live campaigns. | Naitik